Cross border cooperation Programme Albania-Kosovo* under the Instrument for Pre-Accession Assistance (IPA II) allocations for

2014-2015

Project: “Improving tourism in highlands of Albania and Kosovo”

Assignment title: Training of women on marketing of traditional products

# ANNEX II: TERMS OF REFERENCE

CONTENT

ANNEX II: TERMS OF REFERENCE	2

1. BACKGROUND INFORMATION	3

1.1. Partner country	3

1.2. Contracting Authority	3

1.3. About the organization	3

1.4. Country background	3

1.5. About the CBC project Albania and Kosovo	3

2. OBJECTIVE, PURPOSE & EXPECTED RESULTS	4

2.1. Overall objective	4

3. ASSUMPTIONS & RISKS	5

3.1. Assumptions underlying the project	5

3.2. Risks	5

3.3. Geographical area to be covered	5

3.4. Specific work	5

4.3. Project management	6

LOGISTICS AND TIMING	6

5.1. Location	6

5.2. Start date & Period of implementation of tasks	6

REQUIREMENTS	6

6.1. Staff	6

6.2. Office accommodation	7

6.3. Facilities to be provided by the Contractor	7

6.4. Equipment	7

REPORTS	7

7.1. Reporting requirements	7

7.2. Submission and approval of reports	7

MONITORING AND EVALUATION	7

8.1. Definition of indicators	7

8.2. Special requirements	7

# Submitting the Application.....................................................7

# 1. BACKGROUND INFORMATION

## 1.1. Partner country

Republic of Albania; Republic of Kosovo;

## 1.2. Contracting Authority

Albanian Local Capacity Development Federation (ALCDF), Rr. Shyqyri Ishmi, Pll. “Shpresa”, Nr. 22/5 Tirana, Albania

## 1.3. About the organization

The Albanian Local Capacity Development Foundation (ALCDF) is a non-profit organization that focuses on creating innovative solutions in Agriculture, Tourism, Environment, Local Government and Civil Society Developmental in rural areas of Albania. Founded by a group of organizations in 2010, the Foundation has inherited sixteen years of knowledge, expertise, network and capacities from the Netherlands Development Organization (SNV), its predecessor. The goal of ALCDF, is to promote social-economic well-being and viable livelihoods through provision of capacity development services, improved service environments, and increased responsiveness and effectiveness of financing. Additionally, gender equality and female empowerment are top priorities of the Foundation, which is achieved by the several projects implemented. Since its inception, has successfully executed a large number of projects.

## 1.4. Country background

Northern part of Albania and Western part Kosovo share similar resources, cultural and historical background, ethnic diversity, but also face similar problems. Given their natural characteristics and tourism opportunities, the mountain chains in this area have enormous potential for growth, which lays in sectors such as outdoor tourism, hiking & biking, agritourism, cultural tourism etc. Large part of this area has been protected by both Albania and Kosovo as national parks, due to variety of biodiversity and particular natural resources and beauty of these mountains. Economically, both sides of this border suffer from similar issues. The current general economic situation of rural, mountainous area is that of a weak, almost subsistence economy which is heavily reliant on remittances. Unemployment is high and mostly affecting the traditionally weakest sectors of the local society (women, youth, less qualified workers). In Albania and in the remote mountain areas, there is a lack of appreciation for the economic development engine that tourism could be, particularly for employment in an area with otherwise few alternatives. As a result, tourism remains an underdeveloped sector with many constraints.

## 1.5. About the CBC project Albania and Kosovo

Since March 1st, 2018, ALCDF is implementing in partnership with Kosovo Development Centre (KDC) and MRFP the project “Improving tourism offer in highlands of Albania and Kosovo”, funded from the European Union Delegation to Albania.

The main goal of the project is to enhance the capacity and competitiveness of the tourism sector in the cross-border regions by the economic valorisation of its cultural and natural heritage to ensure socio-economic development of the project targeted areas.

The project is conceptualized in two phases that proceed in parallel:

Firstly, improve the infrastructure of shepherd’s huts with the identification and marking of themed trails and info point’s installation will all the necessary information for the tourist and the creation of 5 camping sites and 10 resting points in total.   During the identification process of themed trails will be taken in consideration their vicinity with historical, natural or cultural sites to make the tourists’ journey more appealing.

Secondly, to enhance the capacity of the local farmers to provide good customer service to ensure more opportunities for business and achieve socio-economic goals of the target regions. In full line with the specific objectives that envisage valorisation of cultural and natural heritage as a way to promote the economic development of the target regions we will ensure the improvement of the quality of services and the local farmers’ competitiveness. Furthermore, the cultural, historical and natural heritage will be preserved and promoted.  Following a gender balanced approach, a special emphasis will be given to the women’s vital role in the promotion and development of tourism in the target region. They will be taught to sell traditional products (both artistic and culinary ones) not only to raise the income of their families but also to promote the cultural and culinary peculiarities of the target regions. We will promote both tangible and intangible cultural heritage in terms of marketing, pricing, promotion, product packaging etc. for getting tangible benefits from tourism.

# 2. OBJECTIVE, PURPOSE & EXPECTED RESULTS

## 2.1. Overall objective

The Objective of the assignment is:

We are looking for one (team) of local and national expert (s) to work on this assignment “To train women on marketing of traditional products on Has/Tropoja and Gjakova/Decan/Juniku Municipality (one each) area”.

The goal of this activity is to create promotion capabilities for a target group of women in the area of Has/Tropoja (on the Albanian side) and Gjakova/Decan/Juniku (on the Kosovo side) for production and marketing of local traditional products. The training will be focused on capacity building especially for women dealing with business activities on small scale, concrete demonstration how to do marketing of local traditional products.

Other points may include the handmade traditional products which are not any more in the market nowadays such as production of traditional carpets.

Some points of interest may include folk costumes, traditional food, as well as collection and selling of traditional non-timber forest products. The training will incorporate tradition and marketing with other elements related with tourism development opportunities.

The local or national expert(s) will work closely, in consultation and coordination with the project team.

The expected results and deliverables of this assignment are:

Result(s):

- Emphasize importance of traditional local products in developing tourism in the region together with specific information for each product.

- Increase knowledge and capacities of 40 women (20 in Albania) and (20 in Kosovo) on both sides of the border in regard to local traditional products.

- Stimulate discussions in identifying other traditional product of the CBC area.

- Provide practical and concrete demonstration how to do marketing for local traditional products (concrete successful examples) on both sides of the border conducted.

Deliverable(s):

The expert(s) in consultation with project team members, will ensure the submission of the following materials by the deadlines given:

- Document with the specific information regarding local traditional products for each area/catalogues of local traditional products.

- An agenda and A power point presentation used during training delivery

- Other additional information/handouts/materials related to the topic

- Report for the assignment.

## 2.2. Geographical area to be covered

Albania- Kosovo Kukesi Region (Municipality of Has, Tropoja and Gjakova/Decani/Juniku)

3. Specific Activities of the assignment

## 3.1 Specific work

The expert is required to perform the following functions:

- Become familiar with the project XXXXXXXXXXXXXXXXXXX.

- Collaborate with project team to develop and conduct the training program including:

- Develop and finalise the agenda for the training program based on number of days agreed.

- Design the following:

- The course materials including document and handouts and standard power point presentations. The participants’ materials should be prepared in Albanian.

- Facilitate the training course based on the agreed agenda, objectives, and outputs as well as in accordance with the standards of professional competence and ethical integrity.

- Prepare a report for the training course also including an assessment of participants’ evaluations. The participants’ evaluation should review training content, methods and conduct, practical exercises, and logistical arrangements.

## 3.2 Level of effort

| Description of the activity | Place | Date | N° of working days |
| --- | --- | --- | --- |
| Design the training courses | Office |  | 2 |
| Conduct the training course | Has | 25 October 2018 | 1 |
| Conduct the training course | Gjakove | 29 October 2018 | 1 |
| Training report | Office |  | 2 |

Total number of days is 6 (six) days.

## 4. Project management

## 4.1. Responsible body

Albanian Local Capacity Development Federation (ALCDF), Rr. Shyqyri Ishmi, Pll. “Shpresa”, Nr. 22/5 Tirana, Albania.

## 4.2. Management structure

The project is implemented by following partners: Albanian Local Capacity Development Foundation (ALCDF) as Coordinator and Qendra Kosovare per Zhvilim (KDC) as Co-Beneficiary 1 and Makedonska Razvojna Fondacija za Pretprijatija (MRFP) as Co-Beneficiary 2. ALCDF is responsible for procurement and implementation of this activity for the Albanian side.

### 4.3. Facilities to be provided by the Contracting Authority and/or other parties

The Contracting Authority or/and project partners shall supply the Contractor promptly with any useful information and/or documentation which may be relevant to the performance of the contract.

# LOGISTICS AND TIMING

## 5.1. Location

Albania-  Kosovo Has and Gjakova Region

## 5.2. Start date & Period of implementation of tasks

The intended start date is 22nd of October 2018 and the period of implementation of the contract will be maximum three weeks from this date, 9th of November 2018.

# REQUIREMENTS

## 6.1. Staff

Organizations/expert(s) that are interested to apply for this assignment and expert(s) included in letter of interest should meet the following requirements. Applicants should:

- Have knowledge on the project area

- Proven experience in the field of tourism sector, traditional product promotion, or other relevant field;

- Previous experience related to the topic of interest

The contractor should propose its experts for the assignment. ALCDF requirements about experts’ profile are presented in the table below.

| 1. Experience | Some activity on tourism, business or development sector |
| --- | --- |
| 2. Area of Expertise | - Traditional products marketing, etc other related with women involvement. - Knowledge of the project area - Effective writing and communication skills. |
| 3 Other projects | List of previous projects/ experiences |
| 3. Language skills – written / spoken | Albanian |

Organization’s profile and experts’ CVs should be attached to the Letter of Interest and Financial Offer.

## 6.2. Office accommodation

Office accommodation for the expert working on the contract is to be provided by the Contracting Authority and/or other partners as appropriate.

## 6.3. Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular, it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## 6.4. Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## 7.1. Reporting requirements

The Contractor will submit the above-mentioned deliverables in article 2.

## 7.2. Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# Submitting the Application

All applications must be in Albanian or English. The interested applicants are required to submit a hard copy of the following documents:

- Letter of Interest

- CV(s) of proposed Expert(s)

- Financial Offer

The documents should be enclosed in a sealed envelope and hand delivery or mailed in the following address:

ALCDF – Albanian Local Capacity Development Foundation

Rr, Shyqyri Ishmi, Pallati Shpresa, No. 22/5

Tirana/Albania

Tel: +355 44518628

The Deadline for the submission of application is October 11th, 2018 the latest at 17.30 hours.

For any questions you might have related the application, please contact in the address info@alcdf.org